## Lists (hidden)
CATEGORIES | [6 empty] | STATUS
People | Define Roles & Attributes | Course Needs by Role | Define Performance Standards | Establish Goals | Incentive Plans | Tracking & Reporting | Not Started
Training | Competitive Compensation | Content Development | Schedule & Inspect | High-Impact Activities | Recognition Programs | Tools & Resources | On Track
Coaching | Recruiting & Hiring | Delivery & Schedule | Build Competency | Visibility & Campaigns | Career Development | Accountability | Delayed
Goals & Results | [6 empty] | Off Track
Reinforce & Recognize | [6 empty] | Completed
Performance Management

## Initiative Tracker
Initiative Tracker
For each initiative: What is it? ¦ Why does it matter? ¦ Who owns it? ¦ When is it due? ¦ Status ¦ Investment required?
Category | Sub-Category | Initiative (What) | Why It Matters | Who | When | Status | Investment | Notes / Next Steps | STATUS GUIDE
Not Started
On Track
Delayed
Off Track
Completed

## Example
Initiative Tracker - EXAMPLE
Example: completed tracker showing all six categories, multiple status types, and realistic scenarios.
Category | Sub-Category | Initiative (What) | Why It Matters | Who | When | Status | Investment | Notes / Next Steps | STATUS GUIDE
People | Define Roles & Attributes | Define Role Personas & Hiring Criteria | Ensure consistent expectations across all hiring managers and reduce variability in who gets hired | HR Lead | Mar 2025 | On Track |  | Role framework finalized and distributed to all hiring managers | Not Started
People | Competitive Compensation | Market Compensation Analysis | Address pay gaps to stay competitive and reduce turnover driven by below-market wages | HR Manager | Jun 2025 | Completed | 5000 | External benchmarking study underway — results expected by end of May | On Track
People | Recruiting & Hiring | Rebuild Interview & Onboarding Process | Reduce time-to-productivity for new hires and improve early retention in the first 90 days | Talent Lead | Aug 2025 | On Track |  | On hold pending role definition work — scheduled to begin Q3 | Delayed
Training | Course Needs by Role | Skills Gap Analysis by Position | Align training investment with actual development needs rather than general programs | Training Lead | Feb 2025 | Delayed |  | Results used to build Q2 training calendar and content priorities | Off Track
Training | Content Development | Build New Hire Onboarding Curriculum | Reduce time-to-productivity for new hires from 90 days to 60 with a structured learning path | L&D Manager | May 2025 | Not Started | 8500 | Modules 1 and 2 complete — Module 3 in development, on track for May launch | Completed
Training | Delivery & Schedule | Quarterly Training Calendar — All Roles | Ensure training is scheduled and visible so attendance rates improve across all locations | Training Director | Apr 2025 | On Track | 1200 | Q2 calendar published — enrollment tracking above 80% across all regions
Coaching | Define Performance Standards | Document Coaching Expectations by Role | Give managers a consistent framework and reduce variation in how performance is addressed | Regional Director | Apr 2025 | Delayed |  | Draft shared with three regional managers — feedback slower than expected, pushed two weeks
Coaching | Schedule & Inspect | Weekly 1:1 Coaching Cadence | Catch performance issues early and keep development conversations consistent across the team | Operations Manager | Mar 2025 | Off Track |  | Only 60% of managers completing weekly check-ins — two locations consistently missing
Coaching | Build Competency | Manager Competency Development Program | Develop the next level of leadership capability before it becomes a succession gap | Regional Director | Sep 2025 | Not Started | 6000 | Program design begins Q3 — vendor shortlist in progress
Goals & Results | High-Impact Activities | High-Impact Activity Playbook | Focus team effort on the daily activities that produce the most measurable results | Sales Lead | Jul 2025 | Delayed | 2000 | Additional examples needed before launch — pushed from June to July
Goals & Results | Establish Goals | Define Q3 Team Performance Goals | Align individual contributions to organizational priorities before the quarter begins | VP Operations | Jul 2025 | Not Started |  | Pending Q2 results review — goal-setting workshop scheduled for late June
Goals & Results | Visibility & Campaigns | Performance Visibility Dashboard | Give leaders real-time access to results without manual reporting or delayed data | Analytics Lead | Apr 2025 | On Track | 3500 | Beta running with two regions — full rollout planned for May 1
Reinforce & Recognize | Incentive Plans | Redesign Quarterly Incentive Structure | Current plan does not reinforce the behaviors that drive results — misaligned with strategy | HR Manager | Aug 2025 | Not Started | 12000 | Requires CFO approval before moving forward — proposal submitted April 15
Reinforce & Recognize | Recognition Programs | Launch Peer Recognition Program | Improve team morale and reinforce positive behaviors between formal review cycles | People Ops Lead | May 2025 | On Track | 1500 | Platform selected — rollout planned for June 1 with manager training in May
Performance Management | Tracking & Reporting | Weekly Performance Review Process | Create a consistent cadence for reviewing key metrics so issues surface before they compound | Operations Manager | Mar 2025 | Completed |  | Weekly review now standard in all regional leadership meetings
Performance Management | Accountability | Performance Improvement Framework | Ensure managers have a clear, fair, and documented process before escalating to formal action | HR Manager | Jun 2025 | On Track |  | Framework drafted — manager training scheduled for May