## How to Use
How to Use This Report
Complete the weekly update form once per week. Send to all key stakeholders to keep them informed on the status of the project. Upper management must be informed regularly, and immediately when an initiative is delayed or off track. The report works best right after your weekly team meeting, while the tracker is freshly updated.
Filling It In
| • | Growth Roadmap Pillar and Sub-Category pull from the same lists as the Initiative Tracker. Pick the pillar first. The sub-category dropdown then provides the sub-categories for the chosen pillar.
| • | Overall Status uses the same five values as the Initiative Tracker, so a status never means one thing there and something else here. The cell colors will update based on your status selection.
| • | Original Due never changes once it's set. That column is your honest record of slippage. Forecast is where you say where the date is heading now.
| • | Support Needed is the column upper management wants to hear about. Tell them what they can do to get the project back on track. Leave it empty only when nothing's blocked.
| • | The pillar and sub-category titles live on the Lists tab, and they are starting points rather than fixed values. Overwrite them in the Lists tab with the wording your own Growth Roadmap uses, if different.
Three Habits That Make the Weekly Update Process Work
| • | Send it every week, whether the news is good, bad, or no change.
| • | Keep the distribution list stable. Adding people during a crisis signals panic. Adding them at the start signals confidence.
| • | Never let the report replace a conversation. If something moved to Off Track this week, the report documents it, and you still need to communicate directly to key stakeholders to ensure full awareness.
Printing and Sharing
| • | Print area covers the form only, so the status guide stays on screen and off the page.
| • | Copy the Weekly Update tab each week and rename it by date. A stack of dated tabs becomes a record of how the project moved.
Where This Fits
The Initiative Tracker holds every project, its owner, and where it stands. The Initiative Calendar shows when the work lands across the year. This Initiative Weekly Update report is the third piece: the weekly update you send to the project team and upper management provides regular communication so the people who fund and support your work are kept informed.
Download all three tools at leadership-tools.com/free-project-tracker-template.html

## Weekly Update
Weekly Initiative Update Report
Project / Initiative |  | Owner
Growth Roadmap Pillar |  | Prepared By
Sub-Category |  | Week Ending
Overall Status |  | Target Completion
Key Milestones |  |  |  |  | STATUS GUIDE
Milestone | Owner | Original Due | Forecast | Status | Not Started
On Track
Delayed
Off Track
Completed
Progress This Week |  | Priorities for Next Week
Risks, Issues & Blockers | Owner | Support Needed
Decisions or Approvals Needed From Leadership

## Example
Weekly Initiative Update Report - EXAMPLE
Project / Initiative | Build New Hire Onboarding Curriculum |  | Owner | Marcus Webb, L&D Manager
Growth Roadmap Pillar | Training |  | Prepared By | Marcus Webb
Sub-Category | Content Development |  | Week Ending | Friday, May 8
Overall Status | Delayed |  | Target Completion | June 1
Key Milestones | [5 empty] | STATUS GUIDE
Milestone |  | Owner | Original Due | Forecast | Status | Not Started
Module 1 and 2 content signed off |  | Marcus Webb | Apr 10 | Apr 10 | Completed | On Track
Module 3 draft written |  | Dana Whitfield | Apr 24 | May 6 | Delayed | Delayed
Module 3 review complete |  | Dana Whitfield | May 1 | May 13 | Delayed | Off Track
Pilot group confirmed, six new hires |  | Rachel Ortiz | May 8 | May 8 | Completed | Completed
Pilot session delivered |  | Marcus Webb | Jun 1 | Jun 1 | On Track
Progress This Week |  |  | Priorities for Next Week
Modules 1 and 2 signed off by the regional trainers on Tuesday. Module 3 draft is written but not yet reviewed. Pilot group of six new hires confirmed for June 1. |  |  | Module 3 review with Dana by Wednesday. Book the training room for June 1. Send the pilot invite to all six hires.
Risks, Issues & Blockers |  | Owner | Support Needed
Dana is out until Tuesday, which pushes the Module 3 review to the back half of the week. |  | Marcus Webb | None yet. Flagging it early.
Video editor is not booked. Content budget has not been approved. |  | Marcus Webb | Budget approval by May 15.
June 1 pilot date still holds, but there is no slack left in the schedule. |  | Rachel Ortiz | Hold the training room now.
Decisions or Approvals Needed From Leadership
Approval on the $8,500 content budget by May 15 so we can book the video editor before the June pilot. Sandra is the approver. Proposal went to her on April 15.

## Lists
CATEGORIES | SUB-CATEGORIES | [5 empty] | STATUS
| People | Training | Coaching | Goals & Results | Reinforce & Recognize | Performance Management
People | Define Roles & Attributes | Course Needs by Role | Define Performance Standards | Establish Goals | Incentive Plans | Tracking & Reporting | Not Started
Training | Competitive Compensation | Content Development | Schedule & Inspect | High-Impact Activities | Recognition Programs | Tools & Resources | On Track
Coaching | Recruiting & Hiring | Delivery & Schedule | Build Competency | Visibility & Campaigns | Career Development | Accountability | Delayed
Goals & Results | [6 empty] | Off Track
Reinforce & Recognize | [6 empty] | Completed
Performance Management
Customizing these lists
Overwrite any pillar in column A or any sub-category in columns C through H with your own wording. The dropdowns update automatically. Keep three sub-categories per pillar and keep every entry in the row range shown, or the named ranges will need to be widened under Formulas then Name Manager.