## M.A.P.
Master Action Plan (M.A.P.)
Goal Name: |  |  | Leader Name:
Outcome? (What must be achieved?)
Motivation? (Why is this important?)
High Impact Activities to Achieve Outcome
# | Activity / Task | How Much? | By When? | Owner
1
2
3
4
5
6
Barriers & Solutions
# | Barrier / Obstacle | Solution / Response |  | Comments / Notes
1
2
3
4
5
5-Day Planner / Schedule of High Impact Activities
Describe Activity and Actions to be Achieved
Monday
Tuesday
Wednesday
Thursday
Friday
Weekly Review Notes:

## M.A.P. Example
Master Action Plan (M.A.P.)
Goal Name: | Q3 Customer Service Training Program |  | Leader Name: | Maria Torres, CSM
Outcome? (What must be achieved?)
Design and launch a four-module customer service training program for all 12 team members by September 30, achieving 90%+ completion and a measurable improvement in service quality scores.
Motivation? (Why is this important?)
Our team is inconsistent in handling complex escalations and service challenges — creating customer frustration, rework, and coaching gaps. This training creates a shared standard we can coach to and measure against, directly supporting our satisfaction score and repeat-contact goals.
High Impact Activities to Achieve Outcome
# | Activity / Task | How Much? | By When? | Owner
1 | Define curriculum scope and 4 module topics | Curriculum outline | Jun 15 | M. Torres
2 | Assign content development SMEs for each module | 4 SMEs confirmed | Jun 22 | M. Torres
3 | Build Module 1: Handling Complex Escalations | Training draft complete | Jul 10 | C. Diaz
4 | Build Modules 2–4 (standards, tone, follow-thru) | 3 modules complete | Aug 5 | SME Team
5 | Schedule training sessions with all 12 members | 12 sessions booked | Aug 15 | M. Torres
6 | Deliver all 4 training sessions | 12 members complete | Sep 15 | M. Torres
Barriers & Solutions
# | Barrier / Obstacle | Solution / Response |  | Comments / Notes
1 | Scheduling conflicts during busy season | Book sessions by Aug 15; get manager sign-off early
2 | SME availability for content development | Set firm deadlines in June; weekly SME check-ins
3 | Team engagement and motivation | Use real escalation examples the team has lived through
4 | Training quality inconsistency across sessions | Build facilitator guide; observe Session 1; debrief after
5
5-Day Planner / Schedule of High Impact Activities
Describe Activity and Actions to be Achieved
Monday | Finalize curriculum scope; draft module topics
Tuesday | Meet with SME candidates; confirm 4 assignments
Wednesday | Build Module 1 outline with Chris D.
Thursday | Send all-team preview note re: training launch
Friday | Review week; update plan; confirm Jun 22 deadline
Weekly Review Notes: Are SMEs confirmed and energized? Is Module 1 on track for Jul 10? Any blockers this week?