## How to Use
How to Use This Worksheet
This communication plan worksheet maps the people connected to each initiative you are moving forward and sets a meeting rhythm with each of them, one that keeps everyone informed while keeping in mind your overall calendar of commitments. It is one of the three tools in the Project Prioritization Toolkit. Anything sitting in the top half of your Cost vs Impact Matrix should have at least one stakeholder listed here.
Filling It In
| • | One row is one standing conversation, not one person and not one initiative. If a stakeholder touches three initiatives and you meet with them once, that is a single row. Two separate meetings on two separate days get two rows.
| • | Stakeholder Type changes how you communicate, not just how you sort. A senior leader wants the headline in the first thirty seconds. A support team wants the detail. A business partner wants to know what you need from them and when.
| • | D.A.R.T. is a dropdown, and it colors itself. Pick the category the conversation is mostly about and the cell takes on that color, the same colors used for the Ref numbers on the D.A.R.T. worksheet and the bubbles on the matrix.
| • | Related Initiative(s) is free text, and it accepts more than one. Lead with the reference number from your D.A.R.T. worksheet. When a single conversation covers two initiatives, enter both: R1, D2. Keep your initiative list on the Lists tab to copy from.
| • | Frequency is a negotiation, not a decision you make alone. Some stakeholders want a short conversation every two weeks. Others are fine with monthly or quarterly. Owner is whoever runs the meeting, which is not always you.
| • | Notes is where you record what this person needs from you. What they care about, what they want to see ahead of time, the question they ask every single meeting.
Adding Rows and Sorting
| • | Every header has a filter button. Sort by Stakeholder Type to prepare a round of senior leader updates. Sort by D.A.R.T. to see whether one category is quietly consuming all your attention. Row numbers renumber themselves afterward.
| • | Need more than fifty rows? Copy an existing row rather than inserting a blank one: click its row number, press Ctrl+C or Command+C, then right-click the row number where you want it and choose Insert Copied Cells. A blank inserted row picks up the striping and dropdowns but not the row-number formula.
| • | The strip above the table counts your commitments and converts them into meetings and hours per month. Look at that number before you add another row. Fourteen stakeholders at weekly is fourteen hours a month gone.
Making It Work
| • | When there is nothing meaningful to report, offer to cancel ahead of time. People appreciate it, and it keeps these conversations useful rather than turning them into another calendar item nobody values.
| • | Add the meetings you did not initiate. Standing conversations with key partners belong on this list even when someone else called them, since the point is a complete picture of who you are staying aligned with.
| • | Expect the conversations to improve the work, not just protect it. Share an initiative with another department and you sometimes find they are already halfway toward the same goal, or that someone down the hall has done it before and can save you months.
Printing and Sharing
| • | White cells are yours to fill in. Fifty rows, which runs to about three landscape pages. The column headers repeat at the top of each.
| • | The Example tab maps ten stakeholders to the initiatives used in the D.A.R.T. worksheet example. Delete that tab before sharing if you would rather present a clean sheet.
| • | The dropdown lists live on the Lists tab, alongside a place to keep your initiative list. Overwrite any of it to match the language your organization already uses.
Part of the Project Prioritization Toolkit
Access all three tools, plus the full process behind them, at https://www.leadership-tools.com/how-to-prioritize-work-projects.html

## Communication Plan
Communication Plan Worksheet
One row per standing conversation. Pick a D.A.R.T. category and the cell colors itself. Every header has a filter button for sorting.
MEETING LOAD TOTALS |  | Daily | Weekly | Bi-Weekly | Monthly | Quarterly | As Needed |  | Meetings / Month | Hours at 30 Min Each
|  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
# | Stakeholder Name | Role / Department | Stakeholder Type | D.A.R.T. | Related Initiative(s) | Frequency | Day / Time | Owner | Location | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Example
Communication Plan Worksheet · Example
Ten standing conversations mapped to the initiatives from the D.A.R.T. worksheet example.
MEETING LOAD TOTALS |  | Daily | Weekly | Bi-Weekly | Monthly | Quarterly | As Needed |  | Meetings / Month | Hours at 30 Min Each
|  | 0 | 2 | 3 | 4 | 1 | 0 |  | 18 | 9.2
# | Stakeholder Name | Role / Department | Stakeholder Type | D.A.R.T. | Related Initiative(s) | Frequency | Day / Time | Owner | Location | Notes
1 | Dana Whitfield | VP, Operations | Senior Leader | Attain | A1 · Launch member growth playbook | Bi-Weekly | 2nd and 4th Tue, 9:00am | Sam Ortiz | Admin 350 | Owns the branch rollout. Wants the draft two days ahead of each session.
2 | Marcus Reyes | Director, Technology | Support Team | Table Stakes | T1 · Implement pipeline tracking tool | Weekly | Thu, 1:00pm | Marcus Reyes | Zoom | Integration runs through his team. Cancel when there is no build to review.
3 | Priya Anand | VP, Risk and Security | Peer Department | Table Stakes | T1 · Implement pipeline tracking tool | Monthly | 1st Wed, 10:00am | Sam Ortiz | Admin 423 | Vendor review and data handling sign-off before anything goes live.
4 | Karen Doyle | Branch Manager, Eastside | Team Member | Retain | R1, D2 · Onboarding and meeting quality | Weekly | Mon, 8:30am | Karen Doyle | Her office | Two initiatives, one conversation. Pilot branch for the new handoff, and she runs the Tuesday meeting.
5 | Tom Blaisdell | VP, Marketing | Peer Department | Deepen | D1 · Enhance referral program | Monthly | 3rd Tue, 1:00pm | Sam Ortiz | Admin 350 | Brand approval on anything member facing. Bring mockups, not descriptions.
6 | Angela Ruiz | Member Experience Lead | Team Member | Retain | R2 · Increase relationship depth | Bi-Weekly | 1st and 3rd Fri, 11:00am | Angela Ruiz | Zoom | Owns the product conversation script the tellers use.
7 | Ed Nakamura | Chief Financial Officer | Senior Leader | Attain | A2 · New market outreach campaign | Quarterly | 2nd Thu, 2:00pm | Sam Ortiz | Board Room | Funding gate. He asks for cost per new member every time, so lead with it.
8 | Nate Ellison | Account Manager, Cascade Core | Business Partner | Table Stakes | T1 · Implement pipeline tracking tool | Monthly | 2nd Tue, 3:00pm | Marcus Reyes | Zoom | His release calendar drives our timeline. He called this meeting, not us.
9 | Lisa Moreno | Regional Sales Manager | Peer Department | Table Stakes | T2 · Sales management training | Monthly | 4th Wed, 9:00am | Lisa Moreno | Training Room B | Rolls the coaching standard out to the branch managers.
10 | Grace Okafor | Branch Manager, Northgate | Team Member | Deepen | D2 · Improve meeting quality, add value | Bi-Weekly | 2nd and 4th Fri, 3:00pm | Sam Ortiz | Zoom | Runs the longest meeting in the region and knows it. If the new format works for her, it works anywhere.

## Lists
Dropdown Lists
D.A.R.T. CATEGORIES |  | STAKEHOLDER TYPE | FREQUENCY | INITIATIVE LIST
D | Deepen | Senior Leader | Daily
A | Attain | Peer Department | Weekly
R | Retain | Support Team | Bi-Weekly
T | Table Stakes | Business Partner | Monthly
|  | Team Member | Quarterly
|  | External | As Needed
Customizing these lists
• | The Initiative List starts empty on purpose. Paste your initiatives from the D.A.R.T. Analysis Worksheet, reference number first, and copy from here as you fill in the worksheet.
• | That column has no dropdown by design. It has to accept two references in one cell when a single conversation covers two initiatives, and a dropdown would flag those entries in Google Sheets.
• | Overwrite any Stakeholder Type or Frequency value to match the language your organization already uses. The dropdowns update to match.
• | The four D.A.R.T. categories drive the color on the worksheet. Renaming one is fine. Deleting one leaves that category without a color.