## How to Use
How to Use This Worksheet
The D.A.R.T. Analysis Worksheet is where project prioritization starts. List every initiative you are considering, assign each one a category based on why it matters to the business, and estimate what it will deliver against what it will take. The reference numbers this worksheet produces carry directly into the Cost vs Impact Matrix.
The Four D.A.R.T. Categories
| D | Deepen Relationships. Will this initiative strengthen relationships with existing customers, clients, or team members? These tend to improve loyalty, trust, and the depth of connections you already have.
| A | Attain New Business. Will this help the organization attract new customers, expand its reach, or open new opportunities? Growth work, focused on building what does not yet exist.
| R | Retain Customers. Will this improve the experience of existing customers and help ensure they keep doing business with you? Retention is often where the most leverage sits, since losing a customer costs more than keeping one.
| T | Table Stakes. Is this something the organization must have in place to operate effectively and stay competitive? Table stakes work generates no excitement, though neglecting it creates problems that undermine everything else.
Filling It In
| • | Enter one initiative per row on the D.A.R.T. Analysis tab. If you have completed a Growth Inventory, work straight from that list.
| • | Choose a D.A.R.T. category from the dropdown. Definitions are above. The Ref column fills itself in: your first Deepen initiative becomes D1, the second becomes D2, and the same pattern applies to A, R, and T.
| • | Impact asks what changes if this initiative succeeds. Think about revenue produced, cost removed, customer experience, team performance, or operational efficiency.
| • | Cost covers everything required to deliver it: time, money, people, and organizational energy. What counts as high or low varies by organization, so estimate against your own situation.
| • | Quadrant fills itself in and colors itself. Once Impact and Cost are both chosen, this column names the zone and takes on that zone's color from the Cost vs Impact Matrix. The dropdowns decide the quadrant; you decide where inside it an initiative sits when you plot the matrix.
| • | Why This Matters is the column that earns its keep. If you cannot put the reason into a sentence or two, that is worth knowing before anyone commits resources to it.
Reading Your Results
| • | Ref numbers carry into the Cost vs Impact Matrix. Plot each initiative by its number rather than rewriting the names, and drop it in the quadrant this worksheet already named.
| • | High or Very High impact paired with Low cost points to a quick win. Aim for two or three and move on them early, since the momentum carries into the harder work.
| • | Check the balance across the four categories. An organization chasing new business while ignoring retention and table stakes is building on an unstable foundation.
| • | Most teams handle three to five active initiatives well. Everything else belongs in a visible backlog you revisit on a regular schedule.
Adding Rows
| • | The row number, Ref, and Quadrant columns are locked so a stray keystroke cannot wipe a formula. Everything else is open, and the sheet carries no password.
| • | To add rows, unlock the sheet first. In Excel open the Review tab and click Unprotect Sheet. In your own Google Sheets open Data, then Protect sheets and ranges, and delete the protection listed there.
| • | Thirty-six rows are provided. If you need more, copy an existing row rather than inserting a blank one. Click the row number of a filled row, press Ctrl+C or Command+C, then right-click the row number where you want it and choose Insert Copied Cells. Clear the copied text afterward.
| • | Copying is what carries the formulas. A blank inserted row picks up the borders and dropdowns, but Excel does not copy formulas into it, so the row number, Ref, and Quadrant would all stay empty. Striping corrects itself either way, since it is applied by rule rather than painted on.
| • | Put the protection back when you are done. In Excel, Review, then Protect Sheet, then OK with the password box left empty. In your own Google Sheets it is optional, since the formulas behave the same either way.
Printing and Sharing
| • | White cells are yours to fill in. The Ref and Quadrant columns calculate on their own, so leave those two alone. The print area covers the worksheet only, which keeps the category key beside it off the page.
| • | The Example tab works twelve initiatives through end to end. Delete that tab before sharing if you would rather present a clean sheet.
| • | Category and level options live on the Lists tab. Overwrite them to match the language your organization already uses.
Part of the Project Prioritization Toolkit
Use this worksheet with the Cost vs Impact Matrix and the Communication Plan Worksheet. Access all three tools, plus the full process behind them, at https://www.leadership-tools.com/how-to-prioritize-work-projects.html

## D.A.R.T. Analysis
D.A.R.T. Analysis Worksheet
Enter one initiative per row and choose a category. The Ref column fills in on its own and carries over to the Cost vs Impact Matrix.
# | Initiative or Project | D.A.R.T. Category | Ref | Impact | Cost | Quadrant | Why This Matters | D.A.R.T. KEY
1 | [7 empty] | D | Deepen Relationships
2 | [7 empty] | A | Attain New Business
3 | [7 empty] | R | Retain Customers
4 | [7 empty] | T | Table Stakes
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## Example
D.A.R.T. Analysis Worksheet · Example
Twelve initiatives worked through end to end. The Ref numbers below are what get plotted on the Cost vs Impact Matrix.
# | Initiative or Project | D.A.R.T. Category | Ref | Impact | Cost | Quadrant | Why This Matters | D.A.R.T. KEY
1 | Enhance referral program | Deepen | D1 | High | Low | Quick Wins | Referred members open more accounts and stay longer. The program has not been refreshed in years and most branch staff never bring it up. | D | Deepen Relationships
2 | Improve meeting quality, add value | Deepen | D2 | Very High | Low | Quick Wins | Weekly team meetings run a full hour and produce very little. A tighter agenda sends everyone back to their desk with something useful. | A | Attain New Business
3 | Strengthen business outreach | Deepen | D3 | Medium | Medium | Delegate or Defer | Commercial relationships get handled reactively today. A standing outreach rhythm would deepen the accounts we already hold. | R | Retain Customers
4 | Launch member growth playbook | Attain | A1 | Very High | High | Strategic Bets | Every branch approaches growth differently. A shared playbook gives a new manager a starting point instead of a blank page. | T | Table Stakes
5 | New market outreach campaign | Attain | A2 | High | Very High | Strategic Bets | Two new communities opened to us this year. Without a deliberate campaign we will not be the first name anyone thinks of.
6 | Build new channel partnerships | Attain | A3 | Medium | High | Pass For Now | Partnerships could open lead sources we do not have. Legal review and contract work make this a long runway.
7 | Improve onboarding experience | Retain | R1 | Very High | Low | Quick Wins | The first three months predict whether a new member stays. Our handoff is inconsistent from one branch to the next.
8 | Increase relationship depth | Retain | R2 | High | High | Strategic Bets | Single-product members leave at a much higher rate. Adding one meaningful product changes the retention picture.
9 | Proactive member outreach | Retain | R3 | Medium | Low | Delegate or Defer | Calling members before they call us catches problems early. Low cost, though the payoff builds slowly.
10 | Implement pipeline tracking tool | Table Stakes | T1 | High | Very High | Strategic Bets | We track opportunities across four different spreadsheets. Nobody trusts the numbers, including me.
11 | Sales management training | Table Stakes | T2 | Medium | Medium | Delegate or Defer | Branch managers coach from instinct. A shared standard makes coaching consistent and reviewable.
12 | Daily production reporting | Table Stakes | T3 | Low | Low | Delegate or Defer | The daily numbers already go out. This is maintenance work that keeps the reporting accurate.

## Lists
Dropdown Lists
D.A.R.T. CATEGORIES |  | IMPACT LEVELS | COST LEVELS
D | Deepen | Low | Low
A | Attain | Medium | Medium
R | Retain | High | High
T | Table Stakes | Very High | Very High
Customizing these lists
• | Overwrite any value above to match the language your organization already uses. The dropdowns on the worksheet update to match.
• | Keep the four D.A.R.T. categories starting with different letters. The Ref column builds its prefix from the first letter of the category you choose.
• | Impact and Cost together decide the Quadrant column, which colors itself to match the matching zone on the Cost vs Impact Matrix. Keep all four level names on both lists.